## Dashboard
PROJECT ESTIMATION DASHBOARD
Fill in the yellow fields below. All other values update automatically.
PROJECT INFORMATION
Project Name |  | E-Commerce Web Application
Client Name |  | Acme Corp
Start Date |  | 2026-04-14
Status |  | Not Started
KEY METRICS
Total Features | Total Hours | Hourly Rate | Project Cost | Timeline (days) | Est. End Date | High Risks | Completion %
RISK-ADJUSTED ESTIMATES
Base Timeline (days)
Risk Buffer (+20%)
Risk-Adjusted Timeline
Risk-Adjusted End Date
COST SCENARIOS
Best Case (0.8x) |  |  | Expected (1.0x) |  |  | Worst Case (1.5x)
FEATURE PRIORITY BREAKDOWN
Priority | Count | Hours
Must Have
Should Have
Could Have
Won't Have

## Feature Breakdown
Feature Name | Complexity | Estimated Hours | Priority | Status | Notes
User Authentication (Login/Register) | High | 16 | Must Have | Done | OAuth + email/password
User Profile Page | Medium | 6 | Must Have | In Progress | Avatar upload, edit details
Product Listing Page | Medium | 8 | Must Have | Not Started | Grid/list view, filters
Shopping Cart | High | 14 | Must Have | Not Started | Add/remove, qty update, persist
Checkout & Payment Integration | High | 20 | Must Have | Not Started | Stripe integration
Search & Filtering | Medium | 6 | Should Have | Not Started | Full-text search, category filter
Admin Dashboard | High | 12 | Should Have | Not Started | CRUD for products, orders
Email Notifications | Low | 4 | Should Have | Not Started | Order confirm, shipping update
Product Reviews & Ratings | Medium | 8 | Could Have | Not Started | Star rating, text review
Wishlist / Favorites | Low | 3 | Could Have | Not Started | Save items for later
Social Media Sharing | Low | 2 | Won't Have | Not Started | Share buttons on products
Multi-language Support | High | 18 | Won't Have | Not Started | i18n framework setup
TOTAL ESTIMATED HOURS
Must-Have Hours Only
Completion %

## Timeline Builder
Phase | Start Date | End Date | Duration (days) | Dependencies | Owner | Status | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
Discovery & Requirements | 2026-04-14 |  | 5 | None | Lead Dev | Not Started
UI/UX Design |  |  | 8 | Discovery | Designer | Not Started
Frontend Development |  |  | 15 | Design | Frontend Dev | Not Started
Backend Development |  |  | 15 | Discovery | Backend Dev | Not Started
Integration & Testing |  |  | 10 | Frontend, Backend | Full Team | Not Started
Deployment & Launch |  |  | 3 | Testing | DevOps | Not Started
Buffer |  |  |  | All phases | PM | Not Started
TOTAL PROJECT DURATION
Estimated End Date

## Cost Calculator
PRICING INPUTS
Hourly Rate ($) |  | 95
Total Hours (from Features)
Tax Rate (%) |  | 10%
Platform Fee (%) |  | 5%
Desired Profit Margin (%) |  | 20%
PRICING MODELS
Model | Total Price | Description
Hourly Model |  | Hours x Rate
Fixed Price Model |  | Hourly + Profit Margin
Value-Based Model |  | Fixed + 50% value premium
COST BREAKDOWN (FIXED PRICE)
Subtotal (Hours x Rate)
Profit Margin
Subtotal + Margin
Taxes
Platform Fees
TOTAL PROJECT COST
WHAT-IF SCENARIOS
Scenario | Multiplier | Hours | Total Cost
Best Case (optimistic) | 0.8
Expected Case | 1
Worst Case (pessimistic) | 1.5

## Risk Register
Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Owner | Status
Scope creep - client adds features mid-project | High | High |  | Define clear scope in contract; use change request process | PM | Open
Key team member unavailable | Medium | High |  | Cross-train team; document all decisions | PM | Open
Third-party API changes or goes down | Medium | Medium |  | Use abstraction layer; have fallback plan | Lead Dev | Open
Client delays feedback/approvals | High | Medium |  | Set SLA for feedback in contract; schedule regular reviews | PM | Open
Underestimated task complexity | High | High |  | Add 20% buffer; break tasks into smaller pieces | Lead Dev | Open
Security vulnerability discovered | Low | High |  | Follow OWASP guidelines; schedule security review | Security | Open
Performance issues at scale | Medium | Medium |  | Load test early; design for scalability from start | Backend Dev | Open
Technology/framework learning curve | Medium | Low |  | Allocate training time; use proven tech stack | Lead Dev | Open
Deployment environment issues | Low | Medium |  | Use staging environment; automate deployments | DevOps | Open
Budget overrun | Medium | High |  | Track hours weekly; flag at 75% budget consumed | PM | Open
RISK SCORE MATRIX
| Low Impact (1) | Med Impact (2) | High Impact (3)
High Prob (3) | 3 | 6 | 9
Med Prob (2) | 2 | 4 | 6
Low Prob (1) | 1 | 2 | 3

## Client Proposal
PROJECT PROPOSAL
Project:
Client:
Date:
Prepared by: |  | [Your Name / Company]
1. PROJECT OVERVIEW
[Describe the project goals, background, and what the client wants to achieve. Keep it concise -- 2-3 paragraphs max. Focus on business outcomes, not technical details.]
2. SCOPE OF WORK
Feature | Priority | Estimated Hours
3. TIMELINE
Phase | Duration (days) | Target Dates
4. DELIVERABLES
1. Complete source code (Git repository access)
2. Deployment to production environment
3. Technical documentation and API reference
4. User guide / admin manual
5. 30 days post-launch bug fix support
6. [Add/modify deliverables as needed]
5. PRICING
Total Estimated Hours
Hourly Rate
Subtotal
Profit Margin
Taxes
TOTAL PROJECT COST
6. TERMS & CONDITIONS
1. Payment: 50% deposit required before work begins, 50% upon completion.
2. Changes: Scope changes require written change request and may affect timeline/cost.
3. Timeline: Dates are estimates based on timely client feedback (48hr turnaround).
4. IP Rights: All intellectual property transfers to client upon final payment.
5. Cancellation: Either party may cancel with 14 days written notice.
6. Confidentiality: Both parties agree to keep project details confidential.
7. [Modify these terms to match your standard contract language.]